## Quarterly Timeline
Quarterly Timeline for E1AG Plan Quarterly Updates
Quarter | Timeframe | Report Due | Review with E1AG Advisory Group
Q1 | July 1st-September 30th | By 2nd week of October | 3rd Wendsday in October
Q2 | October 1st-December 31st | By the 2nd week in January | 3rd Wendsday in Febuary
Q3 | January 1st-March 31st | By 2nd week in April | 3rd Wendsday in April
Q4 | April 1st-June 30th | By 2nd week in July | 3rd Wendsday in August

## Quarterly Updates
Division of Developmental Services: Employment First Project Plan
FY 2024-2026
North Star: Increase employment for individuals with DD, SMI and SUD
GOAL
Outcome 1: Maintain collaboration between state agencies that facilitate employment for individuals with intellectual and developmental disabilities (ID/DD), Serious Mental Illness (SMI), & Substance Use Disorder (SUD)
BENCHMARKS FOR SUCCESS
Individual Agency policy difference do not impede provision of services to individuals; Memorandums of Understanding that include commitment to efforts to colloborate and resolve differences and inconsistencies; Alignment of state regulation and administrative policy with Employment First policies and values
GOAL | PARTY RESPONSIBLE & INTERDEPENDENCIES | OUTCOMES | SUPPORT ACTIVITIES | REPORTING METHOD | DATE DUE
1.1 Collaboration between state agencies to develop policies that do not impede employment services of the targeted population. | DBHDS, DMAS, DARS, VDOE, & VCU | 1.1.a Identify data collected from all agencies that can be incorporated into the semi-annual data reports to provide a more comprehensive picture of transition and employment | 1.1.a.i Review all data collected | N/A
|  |  | 1.1.a.ii Identify data that best represents the system | N/A
|  |  | 1.1.a.iii Update semi-annual report to include additional identified data | Semi-Annual Report
| DBHDS, DMAS, DARS, VDOE | 1.1.b. DBHDS collaborating with DARS, DMAS, VDOE regarding the IPS ASPIRE Grant for Serious Mental Illness (SMI) Population | 1.1.b.i Participate in all meetings, trainings | Attendance Records
|  |  | 1.1.b.ii Participate in Fidelity Reviews | Fidelity reports
|  |  | 1.1.b.iii Provide information for grant reporting | Emails
GOAL | PARTY RESPONSIBLE & INTERDEPENDENCIES | OUTCOMES | SUPPORT ACTIVITIES | REPORTING METHOD | DATE DUE
| DBHDS, DARS, VDOE, DMAS | 1.1.c. DBHDS Collaborating with DARS & SME's Griffin and Hammis regarding Customized Employment (CE) | 1.1.c.i Finalize proficiency training and organizational mentoring | Video Library and Documents
|  |  | 1.1.c.ii Identify ways to increase provider capacity; | Provider Development Plan
|  |  | 1.1.c.iii Establish a fidelity review process | Fidelity Tool
1.1.c.iv Review Value Based Purchasing options and ways to ensure financial stability of the EBP
| DBHDS, DARS, VDOE, DMAS | 1.1.c. DBHDS Collaborating with DARS & DOE and SMEs regarding EPIC grant | 1.1.c.i Participate in Meetings and trainings | N/A
|  |  | 1.1.c.ii Work with team to increase access to supports and services to increase CIE; | N/A
|  |  | 1.1.c.iii Report data from EPIC project in the semi-annual employment data report | Semi-Annual Report
Quarterly Summary: Quarter 1: DBHDS worked with the Employment First Advisory Group to finalize the Employment First Plan. DBHDS identified the members of the Interagency workgroup and the members will beging meeting during the third quarter to review the workplan goals and establish the things that need to be accomplished. DBHDS developed a MOU that is being worked through the administration for signature. Quarter 2: DBHDS is working with Procurement office to finalized and have MOU signed between DBDHS and DARS. Quarter 3: The MOU has been finalized between DARS and DBHDS.
GOAL
Outcome 2: Consistent understanding of community-based employment by stakeholders throughout Commonwealth to support Virginia’s Employment First Initiative.
BENCHMARKS FOR SUCCESS
Tools and trainings that help stakeholders to have meaningful conversations that lead to employment; Increase capacity and competence of employment providers (school, CSB, ESO, etc.)
GOAL | PARTY RESPONSIBLE & INTERDEPENDENCIES | OUTCOMES | SUPPORT ACTIVITIES | REPORTING METHOD | DATE DUE
2.1 Provide training consistent with the best practices in the field of employment | DBHDS | 2.1.a Ensure case Managers have the most current information on employment and employment supports and services. | 2.1.a.i Review previously developed training material for case managers and update if needed. | N/A
|  |  | 2.1.a.ii Identify any gaps in training materials for case managers, | List of Gaps
|  |  | 2.1.a.iii Develop training to fill in the gaps; | Training Materials
2.1.a.iv Distribute training and FAQ with memo.
GOAL | PARTY RESPONSIBLE & INTERDEPENDENCIES | OUTCOMES | SUPPORT ACTIVITIES | REPORTING METHOD | DATE DUE
| DBHDS | 2.1.b Ensure providers of services understand the benefits of employment and do not discourage participation in employment based on Myths and Misconceptions | 2.1.b.i Develop appropriate training material for providers | Training Materials
|  |  | 2.1.b.ii Create FAQ; | FAQ
2.1.b.iv Distribute training and FAQ with memo.
| Training Committee | 2.1.c Ensure people with developmental disabilities and their families understand the benefits of employment as well as common myths and misconceptions | 2.1.b.i Develop appropriate training material for providers | Training Materials
|  |  | 2.1.b.ii Create FAQ; | FAQ
2.1.b.iv Distribute training and FAQ with memo.
Quarterly Summary: Quarter 1: DBHDS finalized the workplan and the work goals and is re-stablishing the workgroups related to the training committee. The Committee received updates on work being completed byt the Regional Quality Councils related to Quality Improvement Initiatives. Quarter 2: The Regional Quality Council staff presented two documents for the E1AG to review and provide feedback on related to conversation with 14-17 year olds. A smaller groups of DBHDS, DARS, and DOE staff met offline to finishe review and finalize for alignment with all three agencies epxectations for transition age youth. The team also reviewed and provided feedback related to development of employment outcomes. Quarter 3: The training committte is working on FAQs for the various stakeholders with the top three to five questions related to employment.
GOAL
Outcome 3: Track and analyze existing and new data to increase employment opportunities for the targeted population
BENCHMARKS FOR SUCCESS
Increased number of individuals are employed in competitive integrated employment.
GOAL | PARTY RESPONSIBLE & INTERDEPENDENCIES | OUTCOMES | SUPPORT ACTIVITIES | REPORTING METHOD | DATE DUE
3.2 Develop base line for individuals who receive new waiver slots by 07/2018 that are employed by 12.31.2019 broken down by age | Data Committee | 3.2.a Submit data request to obtain information; | 3.2.a.i Data request submitted; | Semi-Annual Report
|  |  | 3.2..ii Data reviewed; | Semi-Annual Report
|  |  | 3.2.iii Data included in Semi-Annual Report | Semi-Annual Report
3.5 Ensure Appropriate provider capacity across the state to serve indviduuals seeking employment | Data Committee | 3.5.a Identify areas of the state that need additional capacity for employment and develop an implementation plan. | 3.5.a.i Review current providers and capacity; | Survey and Map
|  |  | 3.5.a.iiReview current need; | Survey and Map
|  |  | 3.5.a.iii Identify processes to increase timely access to supports. | Survey and Map
|  | 3.5.b Identify areas of the state that need additional capacity for IPS employment and develop an implementation plan. | 3.5.b.i Review current providers and capacity; | Survey and Map
|  |  | 3.5.b.iiReview current need; | Survey and Map
|  |  | 3..5.b.iii Identify processes to increase timely access to supports. | Survey and Map
|  | 3.5.c Identify areas of the state that need additional capacity for Customized employment and develop an implementation plan. | 3.5.c.i Review current providers and capacity; | Survey and Map
|  |  | 3.5.c.iiReview current need; | Survey and Map
|  |  | 3.5.c.iii Identify processes to increase timely access to supports. | Survey and Map
3.7 Ensure the Commonwealth establishes data targets to meaningfully improve employment outcomes for people with disabilities | Data Committee | 3.7.a Identify data targets for individuals with developmental disabilties | 3.7.a.i Review national trends for employment of people with developmental disabilities.
|  |  | 3.7.a.ii Update targets based on current numbers in comparison to national trends | Semi-Annual Report
|  |  | 3.7.a.iii Identify specific waiver targets for DD in addition to overal target above | Semi-Annual Report
|  | 3.7.b Identify data targets for individuals with SMI | 3.7.b.i Review national trends for employment of people with developmental disabilities. | Semi-Annual Report
|  |  | 3.7.b.ii Identify sources of SMI data between projects with DBHDS , DARS and DOE | Semi-Annual Report
|  |  | 3.7.b.iii Establish targets based on current numbers in comparison to national trends | Semi-Annual Report
|  | 3.7.c Identify data targets for individuals with SUD | 3.7.c.i Review national trends for employment of people with developmental disabilities. | Semi-Annual Report
|  |  | 3.7.c.ii Identify sources of SMI data between projects with DBHDS , DARS and DOE | Semi-Annual Report
|  |  | 3.7.c.iii Establish targets based on current numbers in comparison to national trends | Semi-Annual Report
Quarterly Summary: Quarter 1: The Data Committee met to establish targets for individual with developmental disabilities including waiver targets. Data was collected from employment service organization through September. Quarter 2: The Employment First Advisory Group reviewed the Semi-Annual Data report and reviewed targets related to that data, the process for determining targets was reviewed and vetted. Quarter 3: Data committee reviewed the data from the December data, determined additional information that would like to be received from DARS and will be working to submit a data request to DARS related to this.
GOAL
Outcome 4: Reduce Barriers to Emlpoyment for All Populations
BENCHMARKS FOR SUCCESS
Policy recommendations that lead to increased employment; Best practice implementation guides; Communication mateirals for stakeholders
GOAL | PARTY RESPONSIBLE & INTERDEPENDENCIES | OUTCOMES | SUPPORT ACTIVITIES | REPORTING METHOD | DATE DUE
4.1 Identify barrier to competitive integrated employment for individuals with developmental disabilities | Policy Committee | 4.1.a Develop a plan to address known barriers to employment. | 4.1.a.i Gather information from people with DD, families, support coordinators and providers to identify commonw barriers.
4.1.a.ii Identify potential solutions to those barriers.
4.1.a.iii Identify individuals who can help bust those barriers.
|  |  | 4.1.a.iv Develop plan to address those barriers. | Plan
4.2 Identify barrier to competitive integrated employment for individuals with SMI | Policy Committee | 4.2.a Develop a plan to address known barriers to employment. | 4.2.a.i Gather information from people with SMI, families, support coordinators and providers to identify common barriers.
4.2.a.ii Identify potential solutions to those barriers.
4.2.a.iii Identify individuals who can help bust those barriers.
|  |  | 4.2.a.iv Develop plan to address those barriers. | Plan
4.3 Identify barrier to competitive integrated employment for individuals with SUD | Policy Committee | 4.3.a Develop a plan to address known barriers to employment. | 4.3.a.i Gather information from people with SUD, families, support coordinators and providers to identify common barriers.
4.3.a.ii Identify potential solutions to those barriers.
4.3.a.iii Identify individuals who can help bust those barriers.
|  |  | 4.3.a.iv Develop plan to address those barriers. | Plan
Quarterly Summary: Quarter 1: DBHDS and the Employment First Advisory gorup finalized the plan in the first quarter of the fiscal year and was working to identify members for this workgroup. Workgroup Meetings will begin in the 3rd quarter. Quarter 2: No work started but will be initiated in the third quarter. Quarter 3: The policy committee met and reviewed several topics for then to discuss and prioritize to include policy and practice related to medicaid and vocational rehabilitation, peer mentors in the workplace and other topics.
GOAL
Outcome 5: Assure an active and committed membership that will help advance the Employment First Initiative for all.
BENCHMARKS FOR SUCCESS
Active member participation; Membership representative of all stakeholders
GOAL | PARTY RESPONSIBLE & INTERDEPENDENCIES | OUTCOMES | SUPPORT ACTIVITIES | REPORTING METHOD | DATE DUE
5.1 Assure current guidelines for membership that delineate roles and responsibilities with supporting application | DBHDS | 5.1.a Review and update materials at least annually | 5.1.a.i Review guidelines & E1AG Memebership Application
5.1.a.ii Update as needed.
5.2 Ensure an active and committed membership that is mission driven. | DBHDS | 5.2.a Recruit members that are committed to employment First | 5.2.a.i Review member participation after each meeting.
5.2.a.ii Contact members who missed the meeting an ensure their health, safety and welfare if they did not communicate absence.
5.2.a.iii Maintain information about presence and absence.
5.2.a.iv Communicate with members when absences becoem chronic and determine desire to remain on committee
5.2.a.v Recruit members for vacancies
5.2.a.vi Provide new members with orientation
5.2 Ensure a membership selection committee that is focused on Employment First | DBHDS | 5.3. a Identify members of E1AG willing to sit on membership committee | 5.3.a.i Gather applications and send them to the members identified
5.3.a.ii Provide members with scoring matrix to individually score applications
5.3.a.iii Have members submit score to staff at DBHDS for compilation and discussion at meeting
5.3.a.iv Schedule meeting for committee to scores and selection
5.3.a.v Notify new member of selection and schedule orientation
Quarterly Summary: Quarter 1: Employment First Group requested to review membership application and guidelines prior to requesting additional members and will be reviewing during Q2 meeting. Quarter 2: Employment First Advisory Group reviewed and updated the application for membership, reviewed the guidelines and discussed dibursement of the application and guideline. Application will be ditributed during the 3rd quarter for identification of additional members. Quarter 3: A membership request was sent out to all providers and through the list serv and through various advocacy organizations. The team will review applications in the fourth quarter to add memebers.