## Quarterly Timeline
Quarterly Timeline for E1AG Plan Quarterly Updates
Quarter | Timeframe | Report Due | Review with E1AG Advisory Group
Q1 | July 1st-September 30th | By 2nd week of October | 3rd Wendsday in October
Q2 | October 1st-December 31st | By the 2nd week in January | 3rd Wendsday in Febuary
Q3 | January 1st-March 31st | By 2nd week in April | 3rd Wendsday in April
Q4 | April 1st-June 30th | By 2nd week in July | 3rd Wendsday in August

## Quarterly Updates
Division of Developmental Services: Employment First Project Plan
FY 2021-2023
North Star: Increase employment for individuals with DD, SMI and SUD
GOAL
Outcome 1: Maintain collaboration between state agencies that facilitate employment for individuals with intellectual and developmental disabilities (ID/DD), Serious Mental Illness (SMI), & Substance Use Disorder (SUD)
BENCHMARKS FOR SUCCESS
Individual Agency policy difference do not impede provision of services to individuals; Memorandums of Understanding that include commitment to efforts to colloborate and resolve differences and inconsistencies; Alignment of state regulation and administrative policy with Employment First policies and values
DESIRED OUTCOME & SA Provision | PARTY RESPONSIBLE & INTERDEPENDENCIES | ACTION STEPS | STATUS OF EACH STEP | DOJ REPORTING METHOD | DATE DUE
1.1 Collaboration between state agencies to develop policies that do not impede employment services of the targeted population. | DBHDS, DMAS, DARS, VDOE, & VCU | 1.1.a DBHDS collaborating with DARS, DMAS, VDOE and Workforce regarding technical assistance from VOICE on IPS with SMI/SUD. | 1.1.a.i Policy review and development; | N/A | Project Ended 12/2020
|  |  | 1.1.a.ii Identify agencies to receive technical assistance; | N/A | Project Ended 12/2020
|  |  | 1.1.a.iii Provide technical assistance; | N/A | Project Ended 12/2020
|  |  | 1.1.a.iv Identify ways to incorporate reimbursement. | N/A | Project Ended 12/2020
| DBHDS, DMAS, DARS, VDOE | 1.1.b. DBHDS collaborating with DARS, DMAS, VDOE regarding the IPS ASPIRE Grant for Serious Mental Illness (SMI) Population | 1.1.b.i Policy review and development; |  | On-Going
|  |  | 1.1.b.ii Identify agencies to receive technical assistance; |  | Complete
|  |  | 1.1.b.iii Provide technical assistance; |  | In Progress
1.1.b.iv Identify ways to incorporate reimbursement.
DESIRED OUTCOME & SA Provision | PARTY RESPONSIBLE & INTERDEPENDENCIES | ACTION STEPS | STATUS OF EACH STEP | DOJ REPORTING METHOD | DATE DUE
| DBHDS, DARS, VDOE, DMAS | 1.1.c. DBHDS Collaborating with DARS & SME's Griffin and Hammis regarding Supported Employment Customize Employment (CE) program for Substance Use Disorder (SUD) Population | 1.1.c.i Policy review and development; |  | On Going
|  |  | 1.1.c.ii Identify agencies to receive technical assistance; |  | 07/2022-Complete
|  |  | 1.1.c.iii Provide technical assistance; |  | On-Going
1.1.c.iv Identify ways to incorporate reimbursement.
| DBHDS & DMAS & DARS | 1.1.b DBHDS collaborating with DMAS High Needs Support (HNS) for supported employment. | 1.1.b.i Develop implementation criteria; | N/A | Projected 07/2024; Project has been standstill due to funding 06/2022
|  |  | 1.1.b.ii Develop monitoring criteria; | N/A
|  |  | 1.1.b.iii Resolve worforce concerns. | N/A
|  | 1.1.c DBHDS collaborating with DMAS on HCBS project for Group Supported Employment (GSE) | 1.1.c.i Identify GSE providers for review; |  | Complete
|  |  | 1.1.c.ii Review Providers; |  | On Going
|  |  | 1.1.c.iii Develop technical assistance to come into compliance. |  | On Going
|  | 1.1.d DBHDS collaborating with DARS, VDOE & VCU on pathways to employment for transition aged youth. | 1.1.d.i Develop materials for Case Managers; |  | On Going
1.1.d.ii Develop Materials for teachers;
1.1.d.iii Develop Materials for all other stakeholders.
DESIRED OUTCOME & SA Provision | PARTY RESPONSIBLE & INTERDEPENDENCIES | ACTION STEPS | STATUS OF EACH STEP | DOJ REPORTING METHOD | DATE DUE
1.2 Review interagency Memorandums of Understanding (MOU's) to ensure established outlined commitment to resolve issues and inconsistencies with employment is still meeting the desired needs of all state agencies. | DBHDS, DMAS, DARS, & VDOE | 1.2.a Establish two-year timeline to review agreements. | 1.2.a.i Review MOU; 1.2.a.ii Update MOU. | N/A | 07/2020 & 07/2022
1.3 Maintain collaboration and consistencies of policies, practices, and definitions that are translatable between state agencies, stakeholders, and targeted population of individuals in pre-ets, transition and employment services. | DBHDS, DMAS, DARS, & VDOE | 1.3.a Identify commonly used language at DMAS, DBHDS, DOE and DARS and create a cross reference to the other agency to encourage consistent definitions and terminology among state agencies and stakeholders | 1.3.a.i Create cross walk/reference tool(s); | N/A
1.3.a ii Provide tool(s) to all state agencies.
Outcome 1: 1st Quarter FY 22: DBHDS and DARS updated the MOU for data sharing, IPS, CE and Self-employment implementation. DBHDS, DMAS, and DARS updated MOU regarding individuals and how they access services. DBHDS, DMAS, DOE and DARS all have representative on the IPS workgroup. DMAS continues to collaborate with DBHDS and DARS on the HNS waiver.
Outcome1: 2nd Quarter FY 22: DBHDS & DARS continue to participate in ASPIRE National State Learning Community. HNS program has a changed projection date of implementation from 07/2022 to a projected 07/2024 due to delays in funding. RQC Team for Region 4 in the process of finalizing a cross reference tool for case managers to navigate referrals and services from DARS to DBHDS Waiver funded. CE is currently operating in certain agencies in region 1, due to funding delays. ASPIRE Initiative has started the process review providers & ESO's for the Early adopter program. ASPIRE Initiative has sent a survey out to identify provider and ESO's interest level for the IPS Supported Employment Program. Transition update, NTACT workgroup is developing interactive modules and virtual/ in person listening sessions/town hall.
Outcome 1: 3rd Quarter FY 22: DBHDS & DARS continue to participate in ASPIRE National State Learning Community. ASPIRE has selected two early adopters. HNS program has a changed projection date of implementation from 07/2022 to a projected 07/2024 due to delays in funding. RQC has begun a series of 3 employment training sessions, they just finished the second employment training session.
Outcome 1: 4th Quarter FY 22: DBHDS & DARS continue to paricipate in ASPIRE National State Learning Community. ASPIRE has been working with early adopters on technical assistance and equality of access with IPS. HNS program was not funded by general assembly. RQC finished 3 part employment series.
GOAL
Outcome 2: Consistent understanding of community-based employment by stakeholders throughout Commonwealth to support Virginia’s Employment First Initiative.
BENCHMARKS FOR SUCCESS
Tools and trainings that help stakeholders to have meaningful conversations that lead to employment; Increase capacity and competence of employment providers (school, CSB, ESO, etc.)
DESIRED OUTCOME & SA Provision | PARTY RESPONSIBLE & INTERDEPENDENCIES | ACTION STEPS | STATUS OF EACH STEP | DOJ REPORTING METHOD | DATE DUE
2.1 Revise Case Management Training modules | DBHDS | 2.1.a To align with new expectations of the compliance indicators. | 2.1.a.i Update training information; | N/A | 10/2020;
|  |  | 2.1.a.ii Create FAQ; |  | 2021-06-01
|  |  | 2.1.a.iii Create memo around new training; |  | 6/11/2021 Training Memo: transportation services
|  |  | 2.1.a.iv Distribute training and FAQ with memo. |  | 2021-10-01
| DBHDS | 2.1.b Second Revision of Case Management Training Modules to align with the new expectations of the compliance indicators (4.2020) | 2.1.b.i Update training information; |  | 2021-07-01
|  |  | 2.1.b.ii Create FAQ; |  | 2021-06-01
|  |  | 2.1.b.iii Create memo around new training; |  | 2021-06-30
|  |  | 2.1.b.iv Distribute training and FAQ with memo. |  | 2021-10-01
DESIRED OUTCOME & SA Provision | PARTY RESPONSIBLE & INTERDEPENDENCIES | ACTION STEPS | STATUS OF EACH STEP | DOJ REPORTING METHOD | DATE DUE
| Training Committee | 2.1.c Provide information on the different phases of employment; including how to monitor activities to ensure the individual receiving services and support that is person centered, consistent with standards of service, and that is outlined in the ISP | 2.1.c.i Work with SA to develop quick reference for the different phases of employment; waiver programs as needed. | N/A | 2020-06-04
|  |  | 2.1.c.ii Review and update training regarding allowable employment activities under |  | 10/2021
2.2 Develop reference and resource materials for educators, individuals, families, and stakeholders that support and increase community engagement and employment opportunities | Training Committee | 2.2.a Develop tools and information addressing the target populations: ID/DD, SMI, & SUD to assist in identifying basic work readiness skills to help build interest and confidence when seeking and maintain employment.
| Training Committee | 2.2.b Develop tools and information to address the targeted populations: ID/DD, SMI, & SUD to emphasize the importance of discussions about employment when transition begins under IDEA (age 14+) | 2.2.b.i Review existing process map for families from School to DARS to Waiver, include employment, transitions and HNS if needed | N/A | In Progress
| Training Committee | 2.2.c Develop tools to assist in developing meaningful conversations that can lead to employment for transition aged youth. | 2.2.c.i Create handout on having a discussion with transition age youth;
| DBHDS |  | 2.2.c.ii Update Case Management training.
DESIRED OUTCOME & SA Provision | PARTY RESPONSIBLE & INTERDEPENDENCIES | ACTION STEPS | STATUS OF EACH STEP | DOJ REPORTING METHOD | DATE DUE
| Training Committee | 2.2.d Develop information and tools to access Community Engagement Services that lead to employment. | 2.2.d.i Review existing one page handouts for regional trainings for advocacy. | N/A | 12.11.2020 reviewed for providers & Desk Reference for the phases of employment
2.3 Identify targeted audiences that impact pathways to employment for transition age youth | Training Committee | 2.3.a Identified 13 audiences that impact pathways to employment: Teachers, Case Managers, Individuals, Families, Advocacy, Higher Education, Social Services, Business, legislators, ESO, Day Support, Residential, & DJJ | 2.3.a.i Inquire with the committee if behavioral health and peer recovery specialist need to be added to this audience for transitions. | N/A | 03/2020
2.4 Define each audience and their role involved for transition age youth for pathways to employment | Training Committee | 2.4.a Teachers & Social Services | 2.4.a.i Develop Outline showing pathways | N/A | 2020-03-01
| Training Committee | 2.4.b Case Managers & Residential | 2.4.b.i Develop Outline showing pathways | N/A | 2021-07-01
| Training Committee | 2.4.c Individuals, Families & Businesses | 2.4.c.i Develop Outline showing pathways | N/A | 2020-07-01
| Training Committee | 2.4.d Advocacy & Higher Education | 2.4.d.i Develop Outline showing pathways | N/A | 2020-07-01
| Training Committee | 2.4.e Legislators | 2.4.e.i Develop Outline showing pathways | N/A | Removed
| Training Committee | 2.4.f ESO's & DJJ | 2.4.f.i Develop Outline showing pathways | N/A | 2020-07-01
| Training Committee | 2.4.g Day Support | 2.4.g.i Develop Outline showing pathways | N/A | 2020-07-01
2.5 Create a framework that outlines different components need for transition age youth to pursue pathways to employment | Training Committee |  |  | N/A | 03/2022
2.6 Create a comprehensive reference documents, access guides, fact sheets, and templates to illustrate pathway to employment in the framework. | Training Committee |  | 2.6.a.i. Gather existing resources |  | In progress
DESIRED OUTCOME & SA Provision | PARTY RESPONSIBLE & INTERDEPENDENCIES | ACTION STEPS | STATUS OF EACH STEP | DOJ REPORTING METHOD | DATE DUE
|  |  | 2.6.a.ii. Identify updates to exiting resources and outline new resources that need to be developed |  | 10/2022
2.7 Develop quick reference/ access guides/facts sheets and templates for the identified audiences on the pathways to employment |  |  | Waiting for completion of 2.6 |  | 12/2022
2.8 Establish phases of rollout of materials needed for each audience |  |  | Waiting for completion of 2.7 | N/A
Outcome 2: 1st Quarter FY 22 update: The employment modules for case managers was updated. Created a service authorization document for phases of employment and WPA. Developed mapped out documents for outline reference material
Outcome 2: 2nd Quarter FY 22 update: E1AG Education & Training subcommittee has sent out a survey to all stateholder reguarding the finalized outline document for input. Case Management training had a revision that went live 10/1/2021.
Outcome 2:3rd Quarter FY 22 update: E1AG Education & Training subcommittee has finalized the outline document. Best Practices is working on developing best practices incorporating peer specialist in the IPS employment model.
Outcome 2: 4th Quarter FY 22 update: E1AG Education & Training subcommittee has started gathering existing resources and rearranged parts of the plan as they were completed.
GOAL
Outcome 3: Track and analyze existing and new data to increase employment opportunities for the targeted population
BENCHMARKS FOR SUCCESS
Increased number of individuals are employed in competitive integrated employment.
DESIRED OUTCOME & SA Provision | PARTY RESPONSIBLE & INTERDEPENDENCIES | ACTION STEPS | STATUS OF EACH STEP | DOJ REPORTING METHOD | DATE DUE
3.1 Complete existing trend data report | Data Committee | 3.1.a Add additional data; | 3.1.a Trend graphs created | N/A | In Progress
DESIRED OUTCOME & SA Provision | PARTY RESPONSIBLE & INTERDEPENDENCIES | ACTION STEPS | STATUS OF EACH STEP | DOJ REPORTING METHOD | DATE DUE
3.1.b Finalize and put in report format
3.2 Develop base line for individuals who receive new waiver slots by 07/2018 that are employed by 12.31.2019 broken down by age | Data Committee | 3.2.a Submit data request to obtain information; | 3.2.a Data request submitted; |  | 3.2.a Complete;
|  | 3.2.b Review data to establish baseline; | 3.2.b Data reviewed; |  | 3.2.a Complete;
|  | 3.2.c Develop process around data review and quality improvement; | 3.2.c Process in development. |  | In progress
3.2.d Implement quality review process.
3.3 Revise data survey to include consistent and unique identifier | Data Committee | 3.3.a Identify process currently used by providers; 3.3b Is new process needed; 3.3c If yes, how communicated and created going forward? | 3.3.a Reviewed different options including WaMS as unique identifier |  | 4.3.a Complete
3.4 Finalized Automated Data Survey for collection of Employment Data | Data Committee | 3.4.a Review current data submission concerns; | 3.4.a Identified concerns |  | 3.4.a Complete
3.4.b Is this an education or form concern?
3.4.c What strategies can be used to improve?
3.5 Identify areas of the state that need additional capacity and develop an implementation plan. | Data Committee | 3.5.a Review current providers and capacity; 3.5.b Review current need; 3.5.c Identify processes to increase timely access to supports.
3.6 Add new data tables regarding the waiver sub targets and then set goals around the waiver sub targets. | Data Committee | 3.6.a Request data for waiver sub targets;
3.6.b Create graph around sub targets;
3.6.c Review data and make recommendations;
3.7 Develop a data request template to guide request and follow ups | Data Committee | 3.7.a Identify needed elements of data;
3.7.b Develop format for requesting;
3.7.c Develop method of tracking for follow through.
Outcome 3: 1st Quarter FY22 update: Completed a DQV review of employment data, modified the employment data collection document, updated business rules for data collections and summarization.
Outcome 3: 2nd Quarter FY 22 update: Awaiting for data from requested data inquiry for the trend report.
Outcome 3: 3rd Quarter FY 22 update: Awaiting for data from requested data inquiry for the trend report.
Outcome 3: 4th Quarter FY 22 update: Awaiting for data from requested data inquiry for the trend report.
GOAL
Outcome 4: Development and implementation of best practices evidenced based Supported Employment programs for the state of Virginia
BENCHMARKS FOR SUCCESS
Policy recommendations that lead to increased employment; Best practice implementation guides; Communication mateirals for stakeholders
DESIRED OUTCOME & SA Provision | PARTY RESPONSIBLE & INTERDEPENDENCIES | ACTION STEPS | STATUS OF EACH STEP | DOJ REPORTING METHOD | DATE DUE
4.1 Develop best practices framework for Supported Employment (SE) Sustainability | Best Practice Committee | 4.1.a Meet with National Expert; | 4.1.a.i Consult with Allan Bergman; | N/A | 4.1.a.i 04/2020 & 08/2020-Complete
|  |  | 4.1.a.ii Consult with Jackie Pogue; |  | 4.1.a.ii 05/2020-Complete
|  |  | 4.1.a.iii Consult with SELN |  | 4.1.a.iii On Going
|  |  | 4.1.a.iv Consult with Griffin & Hammis |  | 4.1.a.iv On Going
|  |  | 4.1.a.v Consult with Ruth Brock & |  | Complete
4.1.b Gather information for best practice implementation;
4.1.c Create material for advocacy around reimbursement
4.2 Develop best practices framework for High Needs Support (HNS) for employment | Best Practice Committee | 4.2.a Review materials developed by DMAS and contractor; |  | N/A
4.2.b Make recommendations;
4.2.c Participate on work;
4.2.d Identify strategies to market and develop training.
4.3 Develop best practice framework for Customized Employment (CE) sustainability | Best Practice Committee | 4.3.a Review materials developed; |  | N/A
4.3.b Create informational materials;
4.3.c Identify strategies to increase access.
4.4 Develop best practices framework to enhance peer recovery services in supported employment with evidence based model IPS | Best Practice Committee | 4.4.a Review literature around best practice materials; |  | N/A
4.4.b Identify recommendations for improving peer recovery employment;
|  | 4.4.c Identify pilot projects. | 4.4.c.ii ASPIRE Initiative |  | 03/2021-Complete
4.4.c.ii ROES Project
Outcome 4: 1st Quarter Update FY 22: Met with SME on supported employment, IPS, Aspire Grant, review and revised best practices goals to be more cohesive with over arching goal, review and provided feed back on HNS
Outcome 4: 2nd Quarter FY 22 Update: Conducted ASPIRE training for IPS and Peer Recovery collaborated with Peer Recovery Audiences, Employment audiences
Outcome 4: 3rd Quarter Update FY 22: Presented IPS implementation community expert for input on bridging gaps in peer recovery with employment for IPS.
Outcome 4: 4th Quarter FY 22 Update: Worked with DBDHS Peer Recovery Director and put together ROES (Recovery Oriented Employment Services).
GOAL
Outcome 5: Assure an active and committed membership that will help advance the Employment First Initiative for all.
BENCHMARKS FOR SUCCESS
Active member participation; Membership representative of all stakeholders
DESIRED OUTCOME & SA Provision | PARTY RESPONSIBLE & INTERDEPENDENCIES | ACTION STEPS | STATUS OF EACH STEP | DOJ REPORTING METHOD | DATE DUE
5.1 Review employment 1st membership guidelines to assure current | DBHDS | 5.1.a Review guidelines & E1AG Memebership Application | Reviewed in December | N/A | 12/2020-Complete 12/2021-Complete 12/2022
|  | 5.1.b Update as needed. | Reviewed in December |  | 12/2021- Complete 12/2022
5.2 Convene adhoc membership group when new members needed | DBHDS | 5.2.a Gather volunteers; |  |  | 12/2021- Complete
|  | 5.2.b Send out request for members; |  |  | Complete
5.2.c Have members review applications;
5.2.d Select new members.
5.3 Review participation and follow up with members not actively participating | DBHDS | 5.3.a Attendance at each meeting; |  |  | On going
|  | 5.3.b Follow up with anyone who did proactively communicate absence; |  |  | On going
|  | 5.3.c After two absences review guidelines with member and determine continued participation |  |  | On going
Outcome 5: 1st Quarter FY 22 Update: Continue to Assure an active and committed membership that will help advance the Employment First Initiative for all.
Outcome 5: 2nd Quarter FY 22 update: Reviewed member application, reviewed member guidelines. Identified which audiences are needed for membership. Identified Membership committee volunteers.
Outcome 5: 3rd Quarter FY 22 update Requested E1AG membership applications
Outcome 5: 4th quarter FY 22 update: Received applications for memberships, addressing decline in attendance at subcommittee meetings.
Note on F32: Question for Heather: Are these dates still accurate?